## Report
M.R.T. CHALOEM RATCHAMONGKON LINE | [5 empty] | Point No
Contract1 : UNDERGROUND STRUCTURES-SOUTH |  |  | Checked by: __________________ |  |  | LUO09-SB-400K-D1
Contractor: |  | JV BCKT |  |  |  | LUO09-SB-400K-D2
Construction Office: |  | 2 | Rechecked by : _________________ |  |  | LUO09-SB-420K-D1
Subcontractor: |  | LEO JOVIAN |  |  |  | LUO09-SB-420K-D2
Location: |  | BONKAI STATION |  |  |  | LUO09-SB-440K-D1
Type of Instrument & No. : |  | Building Settlement Pts;BS |  |  |  | LUO09-SB-440K-D2
Readout No.: |  | Topcon, AT-G2 |  |  |  | LUO09-SB-450K-D1
Date of Issue : | 2000-01-25 |  |  |  |  | LUO09-SB-450K-D2
Note: BS-5-R-01-03 reinstslled on 20/08/98. | [5 empty] | LUO09-SB-459K-D1
LUO09-SB-459K-D2
|  |  |  | Last Reading | 1999-10-21 | LUO09-SB-460K-D1
[5 empty] | (mm) | LUO09-SB-460K-D2
|  |  |  | BS-5-R-01-01 | -50.89 | LUO09-SB-480K-D1
|  |  |  | BS-5-R-01-02 | -54.38 | LUO09-SB-480K-D2
|  |  |  | BS-5-R-01-03 | -36.94 | LUO09-SB-500K-D1
|  |  |  | BS-5-R-01-04 |  | LUO09-SB-500K-D2
|  |  |  | BS-5-R-01-05 |  | LUO09-SB-520K-D1
LUO09-SB-520K-D2
LUO09-SB-529K-D1
LUO09-SB-529K-D2
LUO09-SB-540K-D1
LUO09-SB-540K-D2
|  |  |  | Initial Reading |  | LUO09-SB-550K-D1
[5 empty] | 1997-03-21 | LUO09-SB-550K-D2
[5 empty] | (m) | LUO09-SB-560K-D1
|  |  |  | BS-5-R-01-01 | 101.156 | LUO09-SB-560K-D2
|  |  |  | BS-5-R-01-02 | 101.4459 | LUO09-SB-580K-D1
|  |  |  | BS-5-R-01-03(20/08/98) | 101.2648 | LUO09-SB-580K-D2
|  |  |  | BS-5-R-01-04 | 101.282 | LUO09-SB-600K-D1
|  |  |  | BS-5-R-01-05 | 102.0105 | LUO09-SB-600K-D2
Note on S28: user: